## Instructions
Prolongation Cost Calculator
Based on the Prolongation Cost Calculator Guidelines – FIDIC Red Book 2017 (Second Edition), unamended General Conditions.
How to use
1. Inputs: enter project data, entitlement type, profit %, dates, EOT days and toggles.
2. Complete the cost sheets: Site_Costs, Insurance_Bonds, Head_Office, Financing, Escalation, Other_Costs (one line per item).
3. Compliance: record the Sub-Clause 20.2 dates and tick off the evidence checklist.
4. Summary: review the reconciliation from gross Cost to the total claim. Zero formula errors are expected; empty rows show "-".
Colour code
Blue on yellow = input cell you may edit
Black = formula (do not overwrite)
Green = link to another sheet (overwrite only if you deliberately want a different value)
Example data
The workbook is pre-filled with the Guidelines worked examples, marked EXAMPLE: site costs total 33,000.00 (15 days × 2,200) and retention financing is 7,397.26 (500,000 × 6% × 90/365). Overwrite or clear the example rows before use.
Key rules built into the formulas
• Claimed amount = quantity × rate × periods × attributable %. Only the incremental, delay-caused share should be claimed.
• Cost periods are entered per line and need not equal the EOT days (Guidelines s.4).
• Insurance/guarantees: an actual endorsement amount overrides the pro-rata estimate.
• Head office: choose one method; actual additional expenditure is the default. Hudson, Emden and Eichleay are comparisons only.
• Escalation is zero where the price risk lies with the Contractor; amounts already adjusted are deducted.
• Summary deducts concurrent-delay reduction and amounts already paid, then adds profit only for Cost Plus Profit.
• Disruption and acceleration are NOT included – quantify them separately (Guidelines s.3).
Important
This is a calculation aid, not legal advice. Entitlement, time limits, profit % and recoverable heads depend on the Particular Conditions, Contract Data and governing law. Verify against the executed contract.

## Inputs
Inputs – project, entitlement and time data
Blue text on yellow = cells you edit. Black = formulas. Green = links from other sheets.
A. Project details
| Project name | Example Power Plant – Package 3
| Contractor | Contractor Ltd
| Employer | Employer Authority
| Claim reference | CLAIM-EOT-007
| Delay event description | Late access to Area B (Site)
| Entitlement Sub-Clause(s) | 2.1 / 8.4 / 20.2 | Sub-Clause(s) granting EOT and payment. Check the Particular Conditions.
| Currency | EUR
B. Entitlement basis
| Entitlement type | Cost | EOT only = no payment; Cost = Cost excl. profit; Cost Plus Profit = Cost + profit % (Sub-Clause 1.1 and the entitlement Sub-Clause).
| Profit % (Contract Data) | 5% | Percentage stated in the Contract Data; 5% applies under the General Conditions if none is stated.
| Day-count basis for annualised costs (days/year) | 365 | Used for interest, premiums and monthly rates.
C. Time data
| Commencement Date | 2025-01-01
| Original Time for Completion | 2026-12-31
| EOT days claimed / determined | 15 | From the delay analysis (Sub-Clause 8.4). EOT days do not automatically equal cost days.
| Revised Time for Completion | 2027-01-15
| Prolongation period start | 2027-01-01 | Default = day after original completion. Overwrite if costs were incurred in a different period (see Guidelines s.4).
| Prolongation period end | 2027-01-15
| Prolongation days | 15
| Original contract period (days) | 730
| Contract Price | 12000000 | Used only for the Hudson / Emden head-office formulae.
D. Adjustments and toggles
| Reduction for Contractor-responsible / concurrent delay (%) | 0% | Applied to gross Cost on the Summary. Set after the delay analysis.
| Include head-office overheads? | Yes
| Include financing costs? | Yes
| Include escalation? | Yes
| Amounts already paid / reimbursed (Variations etc.) | 0 | Deducted on the Summary to prevent double recovery.

## Summary
Prolongation Cost Summary
Currency: EUR ¦ Claim ref: CLAIM-EOT-007
All figures flow from the input sheets. Cost heads before adjustments, then reconciliation to the total claim (Guidelines s.5–6).
Project: Example Power Plant – Package 3 ¦ Event: Late access to Area B (Site)
| Cost head | Source | Amount | % of gross Cost | Chart data
| A. Site establishment & time-related costs |  |  |  | Site time-related | 33000
| Site accommodation & facilities | Site_Costs | 5250 | 9.397% | Insurance & bonds | 1972.6027
| Site management & supervision | Site_Costs | 18000 | 32.22% | Head office | 6000
| Site services & operating expenses | Site_Costs | 3000 | 5.37% | Financing | 7397.2603
| Hired plant & equipment | Site_Costs | 6750 | 12.08% | Escalation | 3000
| Owned plant (additional operating cost) | Site_Costs | 0 | 0% | Subcontractor & other | 4500
| Idle plant / standby | Site_Costs | 0 | 0%
| Temporary works (extended) | Site_Costs | 0 | 0%
| Subtotal A – Site establishment & time-related |  | 33000 | 59.07%
| B. Insurance, bonds & guarantees | Insurance_Bonds | 1972.6027 | 3.531%
| C. Head-office overheads (Actual additional expenditure) | Head_Office | 6000 | 10.74%
| D. Financing costs | Financing | 7397.2603 | 13.24%
| E. Escalation | Escalation | 3000 | 5.37%
| F. Subcontractor & other event-specific costs | Other_Costs | 4500 | 8.054%
| Gross Cost before adjustments |  | 55869.863
| Less: reduction for Contractor-responsible / concurrent delay | Inputs C30 | 0
| Less: amounts already paid / reimbursed | Inputs C34 | 0
| Net recoverable Cost |  | 55869.863
| Add: profit (only if entitlement = Cost Plus Profit) | Inputs C14–C15 | 0
| TOTAL PROLONGATION CLAIM |  | 55869.863
Key indicators
| Entitlement type |  | Cost
| Prolongation days |  | 15
| EOT days claimed |  | 15
| Average total claim per prolongation day |  | 3724.6575
| Sub-Clause 20.2 procedural timing |  | Procedural timing OK
| Evidence checklist completeness |  | 58.33%
| Automatic warning |  | No automatic warnings

## Site_Costs
Site establishment & time-related costs (Guidelines s.2.1–2.2)
Currency: EUR ¦ Claim ref: CLAIM-EOT-007
Enter one line per cost item. Rate basis Lump sum: enter the amount as Rate and 1 as Qty. Attributable % = share of the cost that is genuinely incremental because of the compensable delay.
# | Category | Description | Rate basis | Qty (nr) | Rate per period | Start date | End date | Days | Periods | Gross cost | Attributable % | Claimed | Evidence ref | Notes / mitigation
1 | Site management & supervision | Site management team (PM, CM, engineers) | Day | 1 | 1200 | 2027-01-01 | 2027-01-15 | 15 | 15 | 18000 | 100% | 18000 | Payroll, timesheets | EXAMPLE – overwrite or delete
2 | Site accommodation & facilities | Site facilities and utilities | Day | 1 | 350 | 2027-01-01 | 2027-01-15 | 15 | 15 | 5250 | 100% | 5250 | Rental invoices, utility bills | EXAMPLE – overwrite or delete
3 | Site services & operating expenses | Security and site services | Day | 1 | 200 | 2027-01-01 | 2027-01-15 | 15 | 15 | 3000 | 100% | 3000 | Security contract, invoices | EXAMPLE – overwrite or delete
4 | Hired plant & equipment | Equipment hire (crane) | Day | 1 | 450 | 2027-01-01 | 2027-01-15 | 15 | 15 | 6750 | 100% | 6750 | Hire invoices, delivery notes | EXAMPLE – overwrite or delete
5 | [7 empty] | 0 | 0 | 0 |  | 0
6 | [7 empty] | 0 | 0 | 0 |  | 0
7 | [7 empty] | 0 | 0 | 0 |  | 0
8 | [7 empty] | 0 | 0 | 0 |  | 0
9 | [7 empty] | 0 | 0 | 0 |  | 0
10 | [7 empty] | 0 | 0 | 0 |  | 0
11 | [7 empty] | 0 | 0 | 0 |  | 0
12 | [7 empty] | 0 | 0 | 0 |  | 0
13 | [7 empty] | 0 | 0 | 0 |  | 0
14 | [7 empty] | 0 | 0 | 0 |  | 0
15 | [7 empty] | 0 | 0 | 0 |  | 0
16 | [7 empty] | 0 | 0 | 0 |  | 0
17 | [7 empty] | 0 | 0 | 0 |  | 0
18 | [7 empty] | 0 | 0 | 0 |  | 0
19 | [7 empty] | 0 | 0 | 0 |  | 0
20 | [7 empty] | 0 | 0 | 0 |  | 0
21 | [7 empty] | 0 | 0 | 0 |  | 0
22 | [7 empty] | 0 | 0 | 0 |  | 0
23 | [7 empty] | 0 | 0 | 0 |  | 0
24 | [7 empty] | 0 | 0 | 0 |  | 0
25 | [7 empty] | 0 | 0 | 0 |  | 0
26 | [7 empty] | 0 | 0 | 0 |  | 0
27 | [7 empty] | 0 | 0 | 0 |  | 0
28 | [7 empty] | 0 | 0 | 0 |  | 0
29 | [7 empty] | 0 | 0 | 0 |  | 0
30 | [7 empty] | 0 | 0 | 0 |  | 0
31 | [7 empty] | 0 | 0 | 0 |  | 0
32 | [7 empty] | 0 | 0 | 0 |  | 0
33 | [7 empty] | 0 | 0 | 0 |  | 0
34 | [7 empty] | 0 | 0 | 0 |  | 0
35 | [7 empty] | 0 | 0 | 0 |  | 0
36 | [7 empty] | 0 | 0 | 0 |  | 0
37 | [7 empty] | 0 | 0 | 0 |  | 0
38 | [7 empty] | 0 | 0 | 0 |  | 0
39 | [7 empty] | 0 | 0 | 0 |  | 0
40 | [7 empty] | 0 | 0 | 0 |  | 0
Total | [9 empty] | 33000 |  | 33000

## Insurance_Bonds
Insurance, bonds & guarantees (Guidelines s.2.3)
Currency: EUR ¦ Claim ref: CLAIM-EOT-007
Claim only the INCREMENTAL cost of the extension. If you hold the actual endorsement / bank advice amount, enter it in column I – it overrides the pro-rata estimate.
# | Type | Description / provider | Annual premium or fee | Original expiry | Revised expiry | Extension days | Pro-rata estimate | Actual additional charge (endorsement) – optional | Amount used | Attributable % | Claimed | Evidence ref | Notes
1 | Performance security | Bank commission – performance guarantee | 48000 | 2026-12-31 | 2027-01-15 | 15 | 1972.6027 |  | 1972.6027 | 100% | 1972.6027 | Bank extension advice | EXAMPLE – overwrite or delete
2 | [5 empty] | 0 | 0 |  | 0 |  | 0
3 | [5 empty] | 0 | 0 |  | 0 |  | 0
4 | [5 empty] | 0 | 0 |  | 0 |  | 0
5 | [5 empty] | 0 | 0 |  | 0 |  | 0
6 | [5 empty] | 0 | 0 |  | 0 |  | 0
7 | [5 empty] | 0 | 0 |  | 0 |  | 0
8 | [5 empty] | 0 | 0 |  | 0 |  | 0
9 | [5 empty] | 0 | 0 |  | 0 |  | 0
10 | [5 empty] | 0 | 0 |  | 0 |  | 0
11 | [5 empty] | 0 | 0 |  | 0 |  | 0
12 | [5 empty] | 0 | 0 |  | 0 |  | 0
13 | [5 empty] | 0 | 0 |  | 0 |  | 0
14 | [5 empty] | 0 | 0 |  | 0 |  | 0
15 | [5 empty] | 0 | 0 |  | 0 |  | 0
16 | [5 empty] | 0 | 0 |  | 0 |  | 0
17 | [5 empty] | 0 | 0 |  | 0 |  | 0
18 | [5 empty] | 0 | 0 |  | 0 |  | 0
19 | [5 empty] | 0 | 0 |  | 0 |  | 0
20 | [5 empty] | 0 | 0 |  | 0 |  | 0
Total | [6 empty] | 1972.6027 |  | 1972.6027 |  | 1972.6027

## Head_Office
Head-office overheads (Guidelines s.2.4)
Currency: EUR ¦ Claim ref: CLAIM-EOT-007
Actual additional expenditure is the most defensible basis. Hudson / Emden / Eichleay are shown for comparison; their use depends on governing law and evidence, and they are not authorised by FIDIC as such.
| Selected method | Actual additional expenditure
| Recovery factor / evidential confidence (%) | 100%
1. Actual additional head-office expenditure
# | Description | Rate basis | Qty (nr) | Rate per period | Start date | End date | Days | Periods | Gross cost | Attributable % | Claimed | Evidence ref
1 | Additional head-office contract management (EXAMPLE) | Day | 1 | 400 | 2027-01-01 | 2027-01-15 | 15 | 15 | 6000 | 100% | 6000 | HO payroll extract
2 | [6 empty] | 0 | 0 | 0 |  | 0
3 | [6 empty] | 0 | 0 | 0 |  | 0
4 | [6 empty] | 0 | 0 | 0 |  | 0
5 | [6 empty] | 0 | 0 | 0 |  | 0
6 | [6 empty] | 0 | 0 | 0 |  | 0
7 | [6 empty] | 0 | 0 | 0 |  | 0
8 | [6 empty] | 0 | 0 | 0 |  | 0
9 | [6 empty] | 0 | 0 | 0 |  | 0
10 | [6 empty] | 0 | 0 | 0 |  | 0
Total | [8 empty] | 6000 |  | 6000
2. Formula methods (comparison only unless selected above)
| Contract Price | 12000000
| Original contract period (days) | 730
| Delay / prolongation days | 15
Hudson
| Head-office overhead % (excluding profit) | 8% | Use the overhead % only, so profit is not added twice when Cost Plus Profit applies.
| Hudson amount | 19726.0274 | Formula: overhead % × Contract Price ÷ contract days × delay days
Emden
| Total head-office overhead of Contractor (period) | 3000000
| Total turnover of Contractor (same period) | 60000000
| Actual head-office overhead % | 5%
| Emden amount | 12328.7671 | Formula: actual overhead % × Contract Price ÷ contract days × delay days
Eichleay
| Contract billings during performance period | 12000000
| Total billings, all contracts (same period) | 60000000
| Total head-office overhead (same period) | 3000000
| Actual performance days (original period + delay) | 745
| Overhead allocable to this contract | 600000
| Daily allocable overhead | 805.3691
| Eichleay amount | 12080.5369 | Formula: daily allocable overhead × delay days
3. Result carried to Summary
| Amount under selected method | 6000
| After recovery factor | 6000
| Included in claim (per Inputs toggle) | 6000

## Financing
Financing costs & delayed release of retention (Guidelines s.2.5)
Currency: EUR ¦ Claim ref: CLAIM-EOT-007
Simple interest: Amount × annual rate × days ÷ day-count basis (Inputs). Entitlement depends on the contract and governing law – do not claim the same financing impact twice.
1. Delayed release of retention
# | Description | Retention amount | Contractual release date | Actual / forecast release date | Delay days | Annual financing rate | Financing cost | Attributable % | Claimed | Evidence / notes
1 | Retention release (EXAMPLE) | 500000 | 2027-02-01 | 2027-05-02 | 90 | 6% | 7397.2603 | 100% | 7397.2603 | Facility statements; matches Guidelines s.2.5 illustration
2 |  |  |  |  | 0 |  | 0 |  | 0
3 |  |  |  |  | 0 |  | 0 |  | 0
4 |  |  |  |  | 0 |  | 0 |  | 0
5 |  |  |  |  | 0 |  | 0 |  | 0
Total | [6 empty] | 7397.2603 |  | 7397.2603
2. Delayed interim payments / other financing
# | Description | Amount delayed | Due date | Date paid | Days late | Annual financing rate | Financing cost | Attributable % | Claimed | Evidence / notes
1 |  |  |  |  | 0 |  | 0 |  | 0
2 |  |  |  |  | 0 |  | 0 |  | 0
3 |  |  |  |  | 0 |  | 0 |  | 0
4 |  |  |  |  | 0 |  | 0 |  | 0
5 |  |  |  |  | 0 |  | 0 |  | 0
6 |  |  |  |  | 0 |  | 0 |  | 0
7 |  |  |  |  | 0 |  | 0 |  | 0
8 |  |  |  |  | 0 |  | 0 |  | 0
9 |  |  |  |  | 0 |  | 0 |  | 0
10 |  |  |  |  | 0 |  | 0 |  | 0
Total | [6 empty] | 0 |  | 0
| Total financing costs claimed (to Summary) | [7 empty] | 7397.2603
Format as in section 1 (no example row – leave blank if not claimed).

## Escalation
Escalation of labour, materials & other prices (Guidelines s.2.6)
Currency: EUR ¦ Claim ref: CLAIM-EOT-007
Escalation is only claimed where caused by the compensable delay and not allocated to the Contractor. Deduct anything already paid under price adjustment (Sub-Clause 13.8).
# | Description of affected work / resource | Base cost at original price level | Escalation % | Escalation amount | Already adjusted / paid under price adjustment | Price risk allocated to Contractor? | Attributable % | Claimed | Evidence ref | Notes
1 | Concrete frame labour re-rate – activity executed 15 days later (EXAMPLE) | 150000 | 2% | 3000 | 0 | No | 100% | 3000 | Revised subcontract rates
2 |  |  |  | 0 |  |  |  | 0
3 |  |  |  | 0 |  |  |  | 0
4 |  |  |  | 0 |  |  |  | 0
5 |  |  |  | 0 |  |  |  | 0
6 |  |  |  | 0 |  |  |  | 0
7 |  |  |  | 0 |  |  |  | 0
8 |  |  |  | 0 |  |  |  | 0
9 |  |  |  | 0 |  |  |  | 0
10 |  |  |  | 0 |  |  |  | 0
11 |  |  |  | 0 |  |  |  | 0
12 |  |  |  | 0 |  |  |  | 0
13 |  |  |  | 0 |  |  |  | 0
14 |  |  |  | 0 |  |  |  | 0
15 |  |  |  | 0 |  |  |  | 0
Total |  |  |  | 3000 |  |  |  | 3000

## Other_Costs
Subcontractor & other event-specific costs (Guidelines s.2.7–2.8)
Currency: EUR ¦ Claim ref: CLAIM-EOT-007
Subcontractor amounts are only claimed where the underlying entitlement is substantiated (column E = Yes). An invoice alone does not establish the Employer's liability.
# | Category | Description | Amount incurred / contractually payable | Entitlement substantiated? | Attributable % | Claimed | Evidence ref | Notes
1 | Subcontractor claim | Subcontractor X – extended supervision (EXAMPLE) | 4500 | Yes | 100% | 4500 | SC invoice 0123; SC claim notice
2 | [5 empty] | 0
3 | [5 empty] | 0
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0
17 | [5 empty] | 0
18 | [5 empty] | 0
19 | [5 empty] | 0
20 | [5 empty] | 0
21 | [5 empty] | 0
22 | [5 empty] | 0
23 | [5 empty] | 0
24 | [5 empty] | 0
25 | [5 empty] | 0
Total |  |  | 4500 |  |  | 4500

## Compliance
Sub-Clause 20.2 compliance & evidence checklist (Guidelines s.5)
Currency: EUR ¦ Claim ref: CLAIM-EOT-007
Time limits below are the General Conditions defaults (28 / 84 days) – amend if the Particular Conditions differ. Late notice may bar the claim, subject to the contract and governing law.
1. Notice and claim timing
| Date Contractor became aware (or should have become aware) of the event | 2026-06-10
| Date notice of claim given | 2026-06-25
| Days from awareness to notice | 15
| Notice time limit (days) | 28
| Notice status | Within time
| Date fully detailed claim submitted | 2026-08-20
| Days from awareness to fully detailed claim | 71
| Fully detailed claim time limit (days) | 84 | For events with continuing effect, check the interim-claim requirements of Sub-Clause 20.2.
| Fully detailed claim status | Within time
| Overall procedural timing | Procedural timing OK
2. Substantiation / evidence checklist
| Item | Status | Reference / notes
| Copy of notice of claim | Yes
| Contractual entitlement analysis (Sub-Clause, Particular Conditions reviewed) | Yes
| Baseline programme | Yes
| Updated / as-built programmes | Yes
| Critical-path delay analysis | No
| Contemporaneous records (site diaries, photos, correspondence) | Yes
| Payroll records and timesheets | Yes
| Plant hire invoices / rental agreements | Yes
| Insurance endorsements and bank advices | No
| General-ledger extracts | No
| Subcontractor claims and proof of payment | N/A
| Mitigation evidence (alternatives considered) | No
| Reconciliation of amounts already paid / Variations | No
| Separation of disruption / acceleration claims | N/A
| Checklist completeness (Yes ÷ applicable items) | 58.33%

## Lists
Lookup lists (used by drop-downs and formulas). Edit with care.
Rate basis | Days per period | Yes / No | Entitlement type | Head-office method | Site cost categories | Security / insurance types | Other cost categories | Checklist status
Day | 1 | Yes | EOT only | Actual additional expenditure | Site accommodation & facilities | Project insurance (CAR / TPL) | Subcontractor claim | Yes
Week | 7 | No | Cost | Hudson | Site management & supervision | Performance security | Additional mobilisation | No
Month | 30.4167 |  | Cost Plus Profit | Emden | Site services & operating expenses | Advance payment guarantee | Additional demobilisation | N/A
Lump sum | 1 |  |  | Eichleay | Hired plant & equipment | Retention bond | Testing / commissioning extension
|  |  |  | None | Owned plant (additional operating cost) | Other security | Handover & close-out
[5 empty] | Idle plant / standby |  | Other event-specific cost
Temporary works (extended)